## LOG (Phiếu ECN)
LOG THỰC HIỆN TÍCH HỢP PLM-ERP VỀ PHIẾU ECN (truyền từ PLM: Test-Chạy thử sang ERP: TEST2024)
No | Ngày thực hiện | Ngày hoàn thành | Nội dung | Người thực hiện | Ghi chú
1 | 2025-11-27 | 2025-11-29 | Tìm hiểu CSDL của phiếu ECN trên PLM | #26223 #25575
2 | 2025-11-27 | 2025-12-08 | Viết Aras methd truyền tiêu đề phiếu ECN từ PLM vào DB trung gian sau khi phiếu ECN chuyển trạng thái "Released" | #25575
3 | 2025-12-01 | 2025-12-05 | Tìm hiểu BOMI04, BOMI02 trên ERP | #26223
4 | 2025-12-08 | 2026-01-08 | Viết service thay đổi BOM trên phiếu ECN (Thêm, sửa, xóa) | #26223
5 | 2026-01-08 | 2026-01-10 | Tìm hiểu INVI02, INVI24 trên ERP | #26223
6 | 2026-01-12 | 2026-01-20 | Viết service thay đổi INV trên phiếu ECN | #26223
7 | 2026-01-09 | 2026-01-21 | MIS tự kiểm nghiệm | MIS
8 | 2026-01-21 |  | KaiFa thực hiện kiểm thử | Kaifa | Số lượng đã test tính đến ngày 5/2/2026 : 6
9 | 2026-02-04 | 2026-02-04 | Họp giải quyết 1 số vấn đề của phiếu ECN trong service tích hợp PLM - ERP | MIS Kaifa | Vấn đề trùng mã NVL trong 1 BOM | Kaifa sử dụng phương án 2: sử dụng Mã NVL để truyền sang ERP
[5 empty] | MIS cải thiện ô mã công đoạn trên sản phẩm | Giữ nguyên ô mã công đoạn trên PLM (Chỉ hiển thị trên PLM thay đổi ô DCSX của sản phẩm) Bổ sung ô DCSX để mục đích là là DCSX khi tạo mới sản phẩm
[5 empty] | KaiFa kiểm thử cùng MIS | KaiFa đồng ý hỗ trợ kiểm thử cùng
10 | 2026-02-04 | 2026-02-04 | Tối ưu lại services tích hợp PLM-ERP | #24085
11 | 2026-02-04 | 2026-02-04 | Kiểm thử lại services tích hợp PLM-ERP sau khi tối ưu | #24085, #26223

## X6 (hidden)
WEEKLY MEETING REPORT SCHEDULE X6-2022
No | Date | Time | Detail | Type | Room | Support | Status
1 | 2022-04-04 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
2 | 2022-04-06 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
3 | 2022-04-08 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
4 | 2022-04-13 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
5 | 2022-04-15 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
6 | 2022-04-18 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
7 | 2022-04-20 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
8 | 2022-04-22 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
9 | 2022-04-25 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
10 | 2022-04-27 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
11 | 2022-05-04 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
12 | 2022-05-06 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
13 | 2022-05-09 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
14 | 2022-05-11 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
15 | 2022-05-13 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
16 | 2022-05-16 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
17 | 2022-05-18 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
18 | 2022-05-20 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
19 | 2022-05-23 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
20 | 2022-05-25 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
21 | 2022-05-27 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
22 | 2022-05-30 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
23 | 2022-06-01 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
24 | 2022-06-06 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trung | Completed
25 | 2022-06-08 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed
26 | 2022-06-10 | 6:40 | Video Meeting Microsoft Teams | Nội bộ | Meeting X6 | Mr. Trân | Completed